## Sheet1
Task Name | Status | Priority | Type | Description
Reset character animations on spawn | Suspended | 1 | Bug | Enemies don't reset their animation when they spawn. This occasionally causes them to spawn partway thru an animation, leading to other bugs
Consistent player control when closing menus | Defer? | 1 | Bug | Player sometimes does not regain control after exiting spell craft menu. Less than 50% repro(may require broader reconsideration of UI code)
Refactor UI to use temporary datas and representative infos | Completed | 2 | Tech Debt | Rather than actively changing player data, UI should only make the change upon confirmations
New Tutorial Level (Design) | In Progress | 1 | Task | Design the new tutorial level that will more organically teach the different mechanics of the game
New Tutorial Level (Graybox) | Not Started | 1 | Task | Graybox the new tutorial level when design is complete
Default Spell Names | Completed | 2 | Task | If player does not enter spell name before crafting, a default name is automatically generated and assigned to the spell
NPC reactions upon getting damaged | Completed | 1 | Task | Enemies need to react to receiving hits. Should attempt to find and engage assailant
NPC Hit state/animation | In Progress | 1 | Task | Hitstun state for enemies that have received damage
Redesign shooting system | Defer? | 2 | Change | Magic projectiles are slow and are very hard to hit, especially without AoE. Perhaps raycast and rotate to target is a better choice?
Projectile physics fix | Fixed? | 2 | Change | Projectiles have a tendency to clip past colliders. Need to resolve this somehow.
Limit number of characters that can be spawned with summon | Not Started | 1 | Task | Spell casters (especially players) need to have a hard limit to prevent performance issues/exploits. Could be tied to spell tier
Create lateral animations for damage and movement | In Progress | 2 | Task
Polish to bronze tier animations for test humans | Not Started | 2 | Task
Integrate animations into Blend Trees in Animator | Not Started | 2 | Task
Knock back tiers | Completed | 1 | Bug | Have knockback/power meet certain thresholds before applying force to the character
Bronze tier art pass on magic projectile visuals | Not Started | 2 | Task | Magic projectiles look like ass. Fix this.
Fix UI inventory items > 1 disappearing from view grid | Completed | 1 | Bug
Playtest this motherfucker! | Not Started | 1 | Task | Actually play arena mode
Handling transitioning from damaged state | Completed | 1 | Task | Have AI states uniquely determine if/how to change state when character takes damage
UI Health bar MVP | Completed | 2 | Task
UI Mana bar MVP | Completed | 2 | Task
Highlighted spell slot MVP | Completed | 2 | Task
Searching for target animation(s) | Not Started | 2 | Task
Enemy Health Bar | Not Started | 2 | Task
Enemy World Space UI | Not Started | 2 | Task
Disable craft spell button if spell is not yet valid | Not Started | 2 | Task
Add fade in to intro cinematic | Not Started | 1 | Task
Investigate starting instantly from tutorial cinematic | Defer? | 2
Black screen in CrossScenePersisted Object | Completed | 1 | Task
Split UI to multiple canvases | Not Started | 2 | Task