## Sheet1
Task Name | Status | Priority | Type | Description
Reset character animations on spawn | Suspended | 1 | Bug | Enemies don't reset their animation when they spawn. This occasionally causes them to spawn partway thru an animation, leading to other bugs
Consistent player control when closing menus | Defer? | 1 | Bug | Player sometimes does not regain control after exiting spell craft menu. Less than 50% repro(may require broader reconsideration of UI code)
Refactor UI to use temporary datas and representative infos | Completed | 2 | Tech Debt | Rather than actively changing player data, UI should only make the change upon confirmations
New Tutorial Level (Design) | In Progress | 1 | Task | Design the new tutorial level that will more organically teach the different mechanics of the game
New Tutorial Level (Graybox) | Not Started | 1 | Task | Graybox the new tutorial level when design is complete
Default Spell Names | In Progress | 2 | Task | If player does not enter spell name before crafting, a default name is automatically generated and assigned to the spell
NPC reactions upon getting damaged | Not Started | 1 | Task | Enemies need to react to receiving hits. Should attempt to find and engage assailant
NPC Hit state/animation | Not Started | 1 | Task | Hitstun state for enemies that have received damage
Redesign shooting system | Not Started | 2 | Change | Magic projectiles are slow and are very hard to hit, especially without AoE. Perhaps raycast and rotate to target is a better choice?
Projectile physics fix | Fixed? | 2 | Change | Projectiles have a tendency to clip past colliders. Need to resolve this somehow.
Limit number of characters that can be spawned with summon | Not Started | 1 | Task | Spell casters (especially players) need to have a hard limit to prevent performance issues/exploits. Could be tied to spell tier